## Project Planner
Nutritional Food Database - Gantt Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Develop project plan | 1 | 2 | 2 | 3 | 80%
Define project scope | 2 | 4 | 3 | 5 | 100%
Develop design documentation | 3 | 5 | 4 | 6 | 55%
Import Nutritional food database | 4 | 6 | 5 | 7 | 70%
Clean and validate data | 5 | 8 | 6 | 9 | 85%
Develop desktop application | 6 | 9 | 7 | 10 | 85%
Implement Features | 7 | 11 | 8 | 12 | 60%
Unit testing | 8 | 14 | 9 | 16 | 60%
Integration testing | 9 | 16 | 10 | 18 | 75%
Develop user manual | 10 | 22 | 11 | 25 | 100%
Develop project report | 11 | 28 | 12 | 30 | 60%
Statement Coverage Testing | 12 | 3 | 13 | 4 | 50%
Branch Coverage Testing | 13 | 3 | 14 | 4 | 30%
Testing Report Preparation | 14 | 5 | 15 | 6 | 20%
Activity 15
Activity 16
Activity 17
Activity 18
Activity 19
Activity 20
Activity 21
Activity 22
Activity 23
Activity 24
Activity 25
Activity 26