## Project Planner
Bank System - WBS
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Assign project manager | 1 | 1 |  |  | 0%
2. Develop project charter | 2 | 2 |  |  | 0%
3. Create scope plan | 4 | 3 |  |  | 0%
4. Create WBS and schedule | 7 | 2 |  |  | 0%
5. Create procurement plan | 9 | 2 |  |  | 0%
6. Create Project Management Plan | 11 | 3 |  |  | 0%
7. Develop network configuration | 14 | 3 |  |  | 0%
8. Remove all hardware (HW) | 17 | 2 |  |  | 0%
9. Order software (SW) and HW | 19 | 1 |  |  | 0%
10. Install new software on servers | 20 | 3 |  |  | 0%
11. Install new HW and SW on client’s machines | 23 | 4 |  |  | 0%
12. Test new billing system | 27 | 3 |  |  | 0%
13. Status reports | 30 | 1 |  |  | 0%
14. Update plans | 31 | 1 |  |  | 0%
15. Final performance review | 32 | 1 |  |  | 0%
16. Prepare final report | 33 | 1 |  |  | 0%
Activity 17 |  |  |  |  | 0%
Activity 18 |  |  |  |  | 0%
Activity 19 |  |  |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%